## Sheet1
Project Name | Cloud Storage Manager |  | Resources available
Start Date | 2022-04-14 |  | End Date
Project Deliverable | Task | Estimated Hours | Details | Time Devoted
Initiation/ Planning
Feasibility Study/ R&D | Brainstorming on Amazon S3 | 4 | Identify the s3 working process and its linking with external services
| Brainstorming on Dropbox | 5 | Identify the dropbox working process and its linking with external services
| Brainstorming on Drive | 4 | Identify the drive working process and its linking with external services
Database Structure |  | 2 | DB tables needs to be created
Design + API end points
Frontend basic Design | frontend design | 2 | identify suitable libraries and include them
Backend APIs | Backend APIs | 4 | identify the available API endpoints and include them
Development
Backend | basic setup of backend | 1
| Amazon s3 storage connection+linking | 5
| Dropbox storage connection+linking | 7
| Drive storage connection+linking | 5
| edit/save the login details for each storage | 2
Frontend | basic setup of frontend | 1
| Dashboard | 2
| file management screen | 6
| settings screen | 2
Integration | backend APIs integration | 5
QA
Testing | Backend | 2
| Frontend | 2